## Order
Scenario 4
Single rate for supply + install | [18 empty] | 8000
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 203080000 | Labour charges for installation, testing & commissioning of plumbing & sanitary wares of site toilets. | [8 empty] | Nos | 1 | 8000 | 0 | 0 | 0 | 0 | 8000 | 8000

## Certification
Scenario 4
Single rate for supply + install |  |  | COP-R001 | [15 empty] | 8000 |  |  | 8000 | 0 | 0 | 0 | 0 | 8000
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 203080000 | Labour charges for installation, testing & commissioning of plumbing & sanitary wares of site toilets. | [8 empty] | Nos | 1 | 8000 | 0 | 0 | 0 | 0 | 8000 | 8000 | 100 | 1 | 8000 | 0 | 0 | 0 | 0 | 8000

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No. - HRL/COP/US/96 |  |  |  |  | Date - 26/3/2014
Project Code - |  | 006 |  |  | Not For Payment
Project - |  | Hyatt Regency - Lucknow
Work : | Labour charges for plumbing and sanitory works for staff toilet |  |  | M/s. Uttam Samal
Budget Code - |  |  |  | House No. 1106, Sector-C, Mahanagar, Lucknow
W.O. / P.O. No. & Date - |  |  | CHPL/006/WO/13-14/024 Dated: 15th Feb,2014 | PAN No.:- BFBPS4233Q
Original W.O. Value - |  |  | 8000 | VAT No.:- CST NO- Service Tax No:-
WO Amendment No. - |  |  |  | Invoice No. 126 Dated: 24th March 2013
Amended or WO/PO Value:- |  |  | 8000
Balance Work Yet to be done |  |  | 0
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type - |  |  |  | I
| Certificate No. - |  |  |  | COP-R001
A | Work Done Amount
1 | Net Amount |  |  |  | 8000 | 8000
2 | VAT / CST |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Other Payments |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 8000 | 8000
B | Recoveries -
1 | Recovery of Advance (@13.333%) |  |  |  | 0
2 | Recovery of water Charges for Water Consumed |  |  |  | 0
3 | Recovery of Power ( For Electricity Consumed) |  |  |  | 0
4 | Recovery of Monthly Advance ( if any) |  |  |  | 0
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee |  |  |  | 0
6 | Recovery of Insurance Premium |  |  |  | 0
7 | Debit for Non removing of debris |  |  |  | 0
8 | Retention Amount (as per Contract Conditions 5%) |  |  |  | 0
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous |  |  |  | 0
B | Total Gross Recoveries - |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement |  |  |  | 0
5 | Net Amount of Other Payments |  |  |  | 0
6 | Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 8000 | 8000
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL
CHPL
CHPL
CHPL