## Order
Scenario 4
Single rate for supply + install | [18 empty] | 1310000
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 202010000 | Shoring work- Labour charges for laying the sand bags north west corner of the site for the protection of earth collapse including supply of gunny bags, complete as per instruction by Engineer In charge. | [8 empty] | Nos | 1 | 1310000 | 0 | 0 | 0 | 0 | 1310000 | 1310000

## Certification
Scenario 4
Single rate for supply + install |  |  | COP-R001 | [15 empty] | 1310000 |  |  | 1310000 | 0 | 0 | 0 | 0 | 1310000
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 202010000 | Shoring work- Labour charges for laying the sand bags north west corner of the site for the protection of earth collapse including supply of gunny bags, complete as per instruction by Engineer In charge. | [8 empty] | Nos | 1 | 1310000 | 0 | 0 | 0 | 0 | 1310000 | 1310000 | 100 | 1 | 1310000 | 0 | 0 | 0 | 0 | 1310000

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No. - HRL/COP/ |  |  |  |  | Date - //20
Project Code - |  | 006 |  |  | Not For Payment
Project - |  | Hyatt Regency - Lucknow
Work : | Sand Bag Shoring Works |  |  | M/s Ranga Rao
Budget Code - |  |  |  | 2/158, Vibhav Khand 2, Gomti Nagar, Lucknow-226010
W.O. / P.O. No. & Date - |  |  | CHPL/006/WO/13-14/Site/001, Dated:- 16th July 2013 | PAN No.:- AJQPG3209A
Original W.O. Value - |  |  | 1310000 | VAT No.:- CST NO- Service Tax No:-
WO Amendment No. - |  |  |  | Invoice No dated 11th July 2013
Amended or WO/PO Value:- |  |  | 1310000
Balance Work Yet to be done |  |  | 0
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type - |  |  |  | I
| Certificate No. - |  |  |  | COP-R001
A | Work Done Amount
1 | Net Amount |  |  |  | 1310000 | 1310000
2 | VAT / CST |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Other Payments |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 1310000 | 1310000
B | Recoveries -
1 | Recovery of Advance (@13.333%) |  |  |  | 0
2 | Recovery of water Charges for Water Consumed |  |  |  | 0
3 | Recovery of Power ( For Electricity Consumed) |  |  |  | 0
4 | Recovery of Monthly Advance ( if any) |  |  |  | 0
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee |  |  |  | 0
6 | Recovery of Insurance Premium |  |  |  | 0
7 | Debit for Non removing of debris |  |  |  | 0
8 | Retention Amount (as per Contract Conditions 5%) |  |  |  | 0
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous |  |  |  | 0
B | Total Gross Recoveries - |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement |  |  |  | 0
5 | Net Amount of Other Payments |  |  |  | 0
6 | Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 1310000 | 1310000
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL
CHPL
CHPL
CHPL