## Order
Scenario 1
Imported Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | Service Tax | Other | Installation Rate Total | Amount
1 | 601000000 | Payment Schedule | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | On Start of Project | [8 empty] | Nos | 1 | 40000 | 4120 | 0 | 44120 | 44120
1.2 | 601000000 | After data collection and survey | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944
1.3 | 601000000 | After Submission of Consent to Establish form | [8 empty] | Nos | 1 | 60000 | 7416 | 0 | 67416 | 67416
1.4 | 601000000 | After Submission of form I & IA and conceptual plan for EC | [8 empty] | Nos | 1 | 90000 | 11124 | 0 | 101124 | 101124
1.5 | 601000000 | After obtaining Environmental Clearance from SEIAA,MoEF, State PCB ETC as required | [8 empty] | Nos | 1 | 70000 | 8652 | 0 | 78652 | 78652
1.6 | 601000000 | After obtaining Consent to Establish | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944
1.7 | 601000000 | Monitoring and report submission (Rs 40,000 x 3) | [8 empty] | Nos | 1 | 120000 | 14832 | 0 | 134832 | 134832
1.8 | 601000000 | After obtaining Consent to Operate | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944

## certification
Scenario 1
Imported Supply |  |  | COP-R001 | [16 empty] | 300000 | 36256 | 0 | 336256
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate |  |  |  |  | Certification
[13 empty] | Basic Rate | Service Tax Amount | Other | Installation Rate Total | Amount | COP Percentage | COP Quantity | COP Basic | COP Service TAX | COP Others | COP TOTAL
1 | 601000000 | Payment Schedule | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | On Start of Project | [8 empty] | Nos | 1 | 40000 | 4120 | 0 | 44120 | 44120 | 100 | 1 | 40000 | 4120 | 0 | 44120
1.2 | 601000000 | After data collection and survey | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944 | 100 | 1 | 40000 | 4944 | 0 | 44944
1.3 | 601000000 | After Submission of Consent to Establish form | [8 empty] | Nos | 1 | 60000 | 7416 | 0 | 67416 | 67416 | 100 | 1 | 60000 | 7416 | 0 | 67416
1.4 | 601000000 | After Submission of form I & IA and conceptual plan for EC | [8 empty] | Nos | 1 | 90000 | 11124 | 0 | 101124 | 101124 | 100 | 1 | 90000 | 11124 | 0 | 101124
1.5 | 601000000 | After obtaining Environmental Clearance from SEIAA,MoEF, State PCB ETC as required | [8 empty] | Nos | 1 | 70000 | 8652 | 0 | 78652 | 78652 | 100 | 1 | 70000 | 8652 | 0 | 78652
1.6 | 601000000 | After obtaining Consent to Establish | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 601000000 | Monitoring and report submission (Rs 40,000 x 3) | [8 empty] | Nos | 1 | 120000 | 14832 | 0 | 134832 | 134832 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 601000000 | After obtaining Consent to Operate | [8 empty] | Nos | 1 | 40000 | 4944 | 0 | 44944 | 44944 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:- |  |  |  |  | Date.:- 06/05/2013
Project Code:- |  | 007 |  |  | Not For Payment
Project:- |  | Propose Five Star Hotel at Guwahati
Work: | Environmental Clearance |  |  | Building Environment (I) Pvt. Ltd
Budget Code:- |  |  |  | 603,6th Floor, Sai Sangam Co.Op Society, Plot No.85, Sector-15, Navi Mumbai-400614
W.O. / P.O. No. & Date:- |  |  | CHPL/007/11-12/C-032, Dated: 28/04/2011 | PAN No.:- AAECB1028L
Original W.O. Value:- |  |  | 500000 | VAT No.:- CST NO- Service Tax No:- AAECB1028LSD002
WO Amendment No.:- |  |  |  | Invoice No. 0811-087-032 dated 6th May 2013
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply Amount |  |  |  | 300000 | 300000
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 36256 | 36256
4
5
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 336256 | 336256
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 336256 | 336256
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL