## Order
Scenario 1
Imported Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | Service Tax | Other | Installation Rate Total | Amount
1 | 601000000 | Payment Schedule:- | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | Phase- I | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | 601000000 | On Confirmation of appointment (10%) | [8 empty] | Nos | 1 | 112000 | 11536 | 0 | 123536 | 123536
1.1.2 | 601000000 | Upon receiving of permission for construction (15%) | [8 empty] | Nos | 1 | 168000 | 17304 | 0 | 185304 | 185304
1.1.3 | 601000000 | Monthly Payment during construction (18 Months ) (75%) | [8 empty] | Nos | 1 | 840000 | 86520 | 0 | 926520 | 926520
1.2 | 601000000 | Phase- II | [8 empty] | NIl | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | 601000000 | Upon start of Interior Works (10%) | [8 empty] | Nos | 1 | 56000 | 5768 | 0 | 61768 | 61768
1.2.2 | 601000000 | Upon submission of drawing for completion Certificate (20%) | [8 empty] | Nos | 1 | 112000 | 11536 | 0 | 123536 | 123536
1.2.3 | 601000000 | Upon Receiving of OC (70%) | [8 empty] | Nos | 1 | 392000 | 40376 | 0 | 432376 | 432376

## certification
Scenario 1
Imported Supply |  |  | COP-R001 | [16 empty] | 112000 | 11536 | 0 | 123536
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate |  |  |  |  | Certification
[13 empty] | Basic Rate | Service Tax Amount | Other | Installation Rate Total | Amount | COP Percentage | COP Quantity | COP Basic | COP Service TAX | COP Others | COP TOTAL
1 | 601000000 | Payment Schedule:- | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | Phase- I | [8 empty] | Nil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | 601000000 | On Confirmation of appointment (10%) | [8 empty] | Nos | 1 | 112000 | 11536 | 0 | 123536 | 123536 | 100 | 1 | 112000 | 11536 | 0 | 123536
1.1.2 | 601000000 | Upon receiving of permission for construction (15%) | [8 empty] | Nos | 1 | 168000 | 17304 | 0 | 185304 | 185304 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3 | 601000000 | Monthly Payment during construction (18 Months ) (75%) | [8 empty] | Nos | 1 | 840000 | 86520 | 0 | 926520 | 926520 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 601000000 | Phase- II | [8 empty] | NIl | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | 601000000 | Upon start of Interior Works (10%) | [8 empty] | Nos | 1 | 56000 | 5768 | 0 | 61768 | 61768 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | 601000000 | Upon submission of drawing for completion Certificate (20%) | [8 empty] | Nos | 1 | 112000 | 11536 | 0 | 123536 | 123536 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3 | 601000000 | Upon Receiving of OC (70%) | [8 empty] | Nos | 1 | 392000 | 40376 | 0 | 432376 | 432376 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:- |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 007 |  |  | Not For Payment
Project:- |  | Proposed Five Star Hotel at Guwahati
Work: | Municipal Architect Consultancy Services |  |  | M/s. Banka & Associates
Budget Code:- |  |  |  | 3rd Floor, N.H.Center Point, Bora Services, G.S. Road, Guwahati 781007
W.O. / P.O. No. & Date:- |  |  | CHPL/10-11/P006/C024 Dated- 16th June 2008 | PAN No.:- ACBPB0590P
Original W.O. Value:- |  |  | 1700000 | VAT No.:- CST NO- Service Tax No:-ACBPB0590ST001
WO Amendment No.:- |  |  |  | Invoice No. BA/62/2010-11 dated 18th Jan 2011
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply Amount |  |  |  | 112000 | 112000
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 11536 | 11536
4
5
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 123536 | 123536
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 123536 | 123536
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL