## Order
Scenario 4
Single rate for supply + install
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 501000000 | Excavation upto specified RL for all depths-In Ordinary and hard soils | [8 empty] | Cum. | 9238 | 358 | 0 | 17.6995 | 0 | 0 | 375.6995 | 3470712
2 | 501000000 | Excavation upto specified RL for all depths-InSoft and decomposed rock | [8 empty] | Cum. | 1 | 968 | 0 | 47.8579 | 0 | 0 | 0 | 0
3 | 501000000 | Disposal of excavated materials to dumping ground as arranged by the contractor | [8 empty] | Cum. | 18813 | 112 | 0 | 5.5373 | 0 | 0 | 117.5373 | 2211229
4 | 501000000 | Backfilling with selected approved earth brought from the site excavation | [8 empty] | Cum. | 1 | 153 | 0 | 7.5643 | 0 | 0 | 0 | 0
5 | 501000000 | Backfilling with selected approved earth brought from outside. | [8 empty] | Cum. | 6111 | 389 | 0 | 19.2322 | 0 | 0 | 408.2322 | 2494707
6 | 501000000 | Providing and laying dry stone packing using crushed stone / metal | [8 empty] | Cum. | 1 | 2582 | 0 | 127.6541 | 0 | 0 | 0 | 0
7 | 501000000 | Pre-Constructional Anti-Termite Treatment | [8 empty] | Cum. | 1185 | 215 | 0 | 10.6296 | 0 | 0 | 225.6296 | 267371
8 | 501000000 | Plain Cement Concrete-In Foundation Pits, Footings, Rafts Etc. | [8 empty] | Cum. | 344 | 6515 | 0 | 322.1016 | 0 | 0 | 6837.1016 | 2351963
9 | 501000000 | Plain Cement Concrete-In Plinth Protection | [8 empty] | Cum. | 30 | 6580 | 0 | 325.3152 | 0 | 0 | 6905.3152 | 207159
10 | 501000000 | Plain Cement Concrete- Over Plum Concrete Filling In Basement-3 (As A Levelling Base For Tre-Mix Flooring | [8 empty] | Cum. | 255 | 6723 | 0 | 332.3851 | 0 | 0 | 7055.3851 | 1799123

## Certification
Scenario 4
Single rate for supply + install | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 501000000 | Excavation upto specified RL for all depths-In Ordinary and hard soils | [8 empty] | Cum. | 9238 | 358 | 0 | 17.6995 | 0 | 0 | 375.6995 | 3470712 |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 501000000 | Excavation upto specified RL for all depths-InSoft and decomposed rock | [8 empty] | Cum. | 1 | 968 | 0 | 47.8579 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 501000000 | Disposal of excavated materials to dumping ground as arranged by the contractor | [8 empty] | Cum. | 18813 | 112 | 0 | 5.5373 | 0 | 0 | 117.5373 | 2211229 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 501000000 | Backfilling with selected approved earth brought from the site excavation | [8 empty] | Cum. | 1 | 153 | 0 | 7.5643 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 501000000 | Backfilling with selected approved earth brought from outside. | [8 empty] | Cum. | 6111 | 389 | 0 | 19.2322 | 0 | 0 | 408.2322 | 2494707 |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 501000000 | Providing and laying dry stone packing using crushed stone / metal | [8 empty] | Cum. | 1 | 2582 | 0 | 127.6541 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
7 | 501000000 | Pre-Constructional Anti-Termite Treatment | [8 empty] | Cum. | 1185 | 215 | 0 | 10.6296 | 0 | 0 | 225.6296 | 267371 |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 | 501000000 | Plain Cement Concrete-In Foundation Pits, Footings, Rafts Etc. | [8 empty] | Cum. | 344 | 6515 | 0 | 322.1016 | 0 | 0 | 6837.1016 | 2351963 |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | 501000000 | Plain Cement Concrete-In Plinth Protection | [8 empty] | Cum. | 30 | 6580 | 0 | 325.3152 | 0 | 0 | 6905.3152 | 207159 |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | 501000000 | Plain Cement Concrete- Over Plum Concrete Filling In Basement-3 (As A Levelling Base For Tre-Mix Flooring | [8 empty] | Cum. | 255 | 6723 | 0 | 332.3851 | 0 | 0 | 7055.3851 | 1799123 |  |  | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:-HAMPI/280 |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 002 |  |  | Not For Payment
Project:- |  | Hyatt Place -Hampi
Work: | Supply, Installation, testing & commisioning of low side HVAC work |  |  | M/s Perfect Infra Engineering Ltd.
Budget Code:- |  |  |  | #812, Ground floor, 8th A main, 23 cross, 7 sectors, HSR layout, Bangalore 560095
W.O. / P.O. No. & Date:- |  |  | CHPL/002/WO/10-11/0050 Dated : 19.05.2010 | PAN No.:- AABCP0122A
Original W.O. Value:- |  |  | 6905433 | VAT No.:- 29790851674 CST NO- 27740016613C Service Tax No:- ST/M-11/MRS/REGN/757610
WO Amendment No.:- |  |  |  | Invoice No. BLR-007/2010 dated 22 nd Dec 2010
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply and Installation Amount |  |  |  | 0 | 0
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 0 | 0
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 0 | 0
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL