## ERP
COST MONITOR
PROJECT NAME: |  |  | Hyatt Regency Lucknow
NO OF KEYS | 198
PLOT AREA (SQ.FT.)
BUILT-UP AREA (SQ.FT.) | 27848
BUDGETED COST (Rs.) | 2033254414
BUDGETED COST PER KEY (Rs.) | 10268962
NO OF BAYS | 223
BUDGETED COST PER BAY (Rs.) | 9117733
INCURRED COST TILL DATE (Rs.) | 0
BUDGET CODE | MASTER CODES | COST HEAD DESCRIPTION | Target Budget |  | Purchase/Work Order Number | Name of Agency | Contract value | Cumulative certified till Date | Uncommitted Costs |  |  | Forecast Cost at Completion | Balance Work to be done | Item Used For Datatreis
|  |  | Amount | Cost / Sft |  |  | Incl. Taxes
|  |  | (Rupees) | (Rupees) |  |  | (Rupees) | (Rupees) | Potential Variation | Uncommitted Contract/PO | TOTAL | Rupees | Rupees
|  |  | A | B |  |  | C | D | E | F
A1 | A10000000 | Land Cost | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11 | A11000000 | Land Cost | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
A12 | A12000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 100000000 | Establishment & Preproject Expenses | 10045800 | 361 |  |  | 0 | 0 | 0 | 10045800 | 10045800 | 10045800 | 10045800
101 | 101000000 | Site Office | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 102000000 | Site Fencing & Barricading | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 103000000 | Equipment & Machinery | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 104000000 | Soil Investigation, Land/Site Survey | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 105000000 | Connection Charges For Water And Electricity | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 106000000 | Access Roads | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 107000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 200000000 | Civil & Structure | 604177376 | 21696 |  |  | 0 | 0 | 0 | 604177376 | 604177376 | 604177376 | 604177376
201 | 201000000 | Building Pilling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20101 | 201010000 | Reinforced Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20102 | 201020000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20103 | 201030000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20104 | 201040000 | Structural Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20105 | 201050000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 203000000 | Substructure | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20301 | 203010000 | Earth Work (Including Shore Pilling) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20302 | 203020000 | Plain Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20303 | 203030000 | Reinforced Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20304 | 203040000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20305 | 203050000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20306 | 203060000 | Structural Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20307 | 203070000 | Masonary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20308 | 203080000 | Internal Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20309 | 203090000 | External Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20310 | 203100000 | Waterproofing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20311 | 203110000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 204000000 | Superstructure | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20401 | 204010000 | Plain Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20402 | 204020000 | Reinforced Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20403 | 204030000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20404 | 204040000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20405 | 204050000 | Structural Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20406 | 204060000 | Masonary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20407 | 204070000 | Internal Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20408 | 204080000 | External Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20409 | 204090000 | Waterproofing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20410 | 204100000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 205000000 | External Development Work | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20501 | 205010000 | Roads & Pavements | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20502 | 205020000 | Compound Wall & Gates | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20503 | 205030000 | Storm Water Drain | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 206000000 | Façade | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20601 | 206010000 | Punch Window | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20602 | 206020000 | Structural Glazing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20603 | 206030000 | Canopies & Misc | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20604 | 206040000 | Doors | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20605 | 206050000 | Façade Testing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20606 | 206060000 | Façade Cleaning System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20607 | 206070000 | External Paint | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20608 | 206080000 | Stone Cladding | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20609 | 206090000 | Acp Cladding | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20610 | 206100000 | Façade Lightning | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 207000000 | Landscaping | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20701 | 207010000 | Hardscape | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20702 | 207020000 | Softscape | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 208000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 300000000 | MEP | 363606177 | 13057 |  |  | 0 | 0 | 0 | 363606177 | 363606177 | 363606177 | 363606177
301 | 301000000 | Plumbing & Drainage | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 302000000 | Fire Fightning | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 303000000 | Electrical Work | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 304000000 | Hvac Work | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30401 | 304010000 | Low Side Work | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30402 | 304020000 | Owner Supply Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 305000000 | Ibms Works (Bms & Fire Alarm) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 306000000 | Diesel Generator & Hsd Tank | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 307000000 | Boiler-Hot Water & Mechanical Services | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 308000000 | Sewage Treatment Plant | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 309000000 | Water Treatment Plant | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 310000000 | Gas Bank | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 311000000 | Data & Voice Communication | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 312000000 | Master Antenna & Television | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 313000000 | Public Address System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 314000000 | Closed Circuit Television | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 315000000 | Access Control System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 316000000 | Security Control System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 317000000 | Audio Visual System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 318000000 | Signage | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 319000000 | Transportation | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 320000000 | Mechanical Car Park | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 321000000 | Dimmer | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 322000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 400000000 | Interior & Fitouts | 541290026.9 | 19437 |  |  | 0 | 0 | 0 | 541290026.9 | 541290026.9 | 541290026.9 | 541290026.9
401 | 401000000 | Guest Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40101 | 401010000 | King Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010101 | 401010100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401010101 | 401010101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401010102 | 401010102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401010103 | 401010103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010102 | 401010200 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010103 | 401010300 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010104 | 401010400 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010105 | 401010500 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010106 | 401010600 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40102 | 401020000 | Twin Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010201 | 401020100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401020101 | 401020101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401020102 | 401020102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401020103 | 401020103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010202 | 401020200 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010203 | 401020300 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010204 | 401020400 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010205 | 401020500 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010206 | 401020600 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40103 | 401030000 | SUITES | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010301 | 401030100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401030101 | 401030101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401030102 | 401030102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401030103 | 401030103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010302 | 401030200 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010303 | 401030300 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010304 | 401030400 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010305 | 401030500 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010306 | 401030600 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40104 | 401040000 | Corridor | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010401 | 401040100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401040101 | 401040101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401040102 | 401040102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401040103 | 401040103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010402 | 401040200 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010403 | 401040300 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010404 | 401040400 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010405 | 401040500 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010406 | 401040600 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40105 | 401050000 | Other Miscellaneous Room & Suit | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010501 | 401050100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401050101 | 401050101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401050102 | 401050102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401050103 | 401050103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010502 | 401050200 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010503 | 401050300 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010504 | 401050400 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010505 | 401050500 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010506 | 401050600 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40106 | 401060000 | Mock-Up Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010601 | 401060100 | Shell & Core | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010602 | 401060200 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401060201 | 401060201 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401060202 | 401060202 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401060203 | 401060203 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010603 | 401060300 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010604 | 401060400 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010605 | 401060500 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010606 | 401060600 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010607 | 401060700 | MEP works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010608 | 401060800 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 402000000 | Public Area | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40201 | 402010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4020101 | 402010100 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4020102 | 402010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4020103 | 402010300 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40202 | 402020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40203 | 402030000 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40204 | 402040000 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40205 | 402050000 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40206 | 402060000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 403000000 | BOH Area | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40301 | 403010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4030101 | 403010100 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4030102 | 403010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4030103 | 403010300 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40302 | 403020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40303 | 403030000 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40304 | 403040000 | bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40305 | 403050000 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40306 | 403060000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 404000000 | Commercial Area | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40401 | 404010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4040101 | 404010100 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4040102 | 404010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4040103 | 404010300 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40402 | 404020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40403 | 404030000 | Loose Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40404 | 404040000 | Bought Out Item Including Equipment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40405 | 404050000 | Operation Supplies | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40406 | 404060000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 500000000 | OS&E | 40000000 | 1436 |  |  | 0 | 0 | 0 | 40000000 | 40000000 | 40000000 | 40000000
501 | 501000000 | Os And (Linens / Uniforms) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
502 | 502000000 | Chinaware / Glassware / Silverware, Utensils, Staff Dinning | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
503 | 503000000 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50301 | 503010000 | Kitchen | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50302 | 503020000 | Laundry | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50303 | 503030000 | Gym & Spa | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50304 | 503040000 | Swimming Pool/Water Feature | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | 504000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 600000000 | Consultancy & Others | 89185680.526 | 3203 |  |  | 0 | 0 | 0 | 89185680.526 | 89185680.526 | 89185680.526 | 89185680.526
601 | 601000000 | Consultancy Fee | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
602 | 602000000 | Travelling Reimbersment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
603 | 603000000 | Hits Fees | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
604 | 604000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 700000000 | Contingency | 242879265.574 | 8722 |  |  | 0 | 0 | 0 | 242879265.574 | 242879265.574 | 242879265.574 | 242879265.574
701 | 701000000 | Contingency | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
702 | 702000000 | Escalation | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 800000000 | Project Running Expenses And Pre Opening Site Expenses | 142070088 | 5102 |  |  | 0 | 0 | 0 | 142070088 | 142070088 | 142070088 | 142070088
801 | 801000000 | Salary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80101 | 801010000 | Site Staff Salary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80102 | 801020000 | Head Office Support Salary/Cost | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
802 | 802000000 | Site Office -Running Expenses (Project Management Expenses) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80201 | 802010000 | Power | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80202 | 802020000 | Generator Set Monthly Operational Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80203 | 802030000 | Telephone | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80204 | 802040000 | Water | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80205 | 802050000 | Machine Operators (Hoists/Levellers Etc) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80206 | 802060000 | Maintenance Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80207 | 802070000 | Safety Provisions | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80208 | 802080000 | Travelling Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80209 | 802090000 | Car Hire Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80210 | 802100000 | Local Conveyance | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80211 | 802110000 | Printing And Stationery | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80212 | 802120000 | Courier Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80213 | 802130000 | Recruitment Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80214 | 802140000 | Housekeeping | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80215 | 802150000 | Training | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80216 | 802160000 | Advertisement | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80217 | 802170000 | Fire Extinguishers | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80218 | 802180000 | Guest House | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80219 | 802190000 | Bank Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80220 | 802200000 | Insurance | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80221 | 802210000 | Legal Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80222 | 802220000 | Liasioning Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80223 | 802230000 | Petrol / Diesel Charges | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80224 | 802240000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
803 | 803000000 | Vehical/Cars | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
804 | 804000000 | Pre-Opening Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
805 | 805000000 | It Cost & Computers | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
806 | 806000000 | Statutory Fees Including Labour Cess | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
807 | 807000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 900000000 | Interest During Construction Period | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
901 | 901000000 | Interest During Construction Period | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
902 | 902000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0