## Order
Scenario 1
Imported Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | Service Tax | Other | Installation Rate Total | Amount
A | 501000000 | Structural Peer review Consultancy | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0
1 | 501000000 | Payment Schedule | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 501000000 | On appoinment (20%) | [8 empty] | Nos | 0.2 | 425000 | 52530 | 0 | 477530 | 95506
1.2 | 501000000 | On reviewing Etabs model and commenting on DBR/piling/Foundation Drawings (30%) | [8 empty] | Nos | 0.3 | 425000 | 52530 | 0 | 477530 | 143259
1.3 | 501000000 | On submitting Interim reports (30%) | [8 empty] | Nos | 0.3 | 425000 | 52530 | 0 | 477530 | 143259
1.4 | 501000000 | On submitting and approval of final report from CHPL (20%) | [8 empty] | Nos | 0.2 | 425000 | 52530 | 0 | 477530 | 95506

## certification
Scenario 1
Imported Supply |  |  | COP-R002 | [16 empty] | 212500 | 26265 | 0 | 238765
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate |  |  |  |  | Certification
[13 empty] | Basic Rate | Service Tax Amount | Other | Installation Rate Total | Amount | COP Percentage | COP Quantity | COP Basic | COP Service TAX | COP Others | COP TOTAL
A | 501000000 | Structural Peer review Consultancy | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 501000000 | Payment Schedule | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 501000000 | On appoinment (20%) | [8 empty] | Nos | 0.2 | 425000 | 52530 | 0 | 477530 | 95506 | 100 | 0.2 | 85000 | 10506 | 0 | 95506
1.2 | 501000000 | On reviewing Etabs model and commenting on DBR/piling/Foundation Drawings (30%) | [8 empty] | Nos | 0.3 | 425000 | 52530 | 0 | 477530 | 143259 | 100 | 0.3 | 127500 | 15759 | 0 | 143259
1.3 | 501000000 | On submitting Interim reports (30%) | [8 empty] | Nos | 0.3 | 425000 | 52530 | 0 | 477530 | 143259 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 501000000 | On submitting and approval of final report from CHPL (20%) | [8 empty] | Nos | 0.2 | 425000 | 52530 | 0 | 477530 | 95506 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:-HAMPI/280 |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 002 |  |  | Not For Payment
Project:- |  | Hyatt Place -Hampi
Work: | Supply, Installation, testing & commisioning of low side HVAC work |  |  | M/s Perfect Infra Engineering Ltd.
Budget Code:- |  |  |  | #812, Ground floor, 8th A main, 23 cross, 7 sectors, HSR layout, Bangalore 560095
W.O. / P.O. No. & Date:- |  |  | CHPL/002/WO/10-11/0050 Dated : 19.05.2010 | PAN No.:- AABCP0122A
Original W.O. Value:- |  |  | 6905433 | VAT No.:- 29790851674 CST NO- 27740016613C Service Tax No:- ST/M-11/MRS/REGN/757610
WO Amendment No.:- |  |  |  | Invoice No. BLR-007/2010 dated 22 nd Dec 2010
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply Amount |  |  | 85000 | 85000 | 85000
2 | VAT |  |  | 10506 | 10506 | 10506
3 | Service Tax. |  |  | 0 | 0 | 0
4
5
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 95506 | 95506
B | Recoveries:-
1 | Recovery of Advance (@13.333%) |  |  | 0
2 | Recovery of water Charges for Water Consumed |  |  | 0
3 | Recovery of Power ( For Electricity Consumed) |  |  | 0
4 | Recovery of Monthly Advance ( if any) |  |  | 0
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee |  |  | 0
6 | Recovery of Insurance Premium |  |  | 0
7 | Debit for Non removing of debris |  |  | 0
8 | Retention Amount (as per Contract Conditions 5%) |  |  | 0
9 | Non Conformity of Concrete |  |  | 0 | 0
10 | Miscellaneous |  |  | 0
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  | 0 | 0
2 | Ad-Hoc Certification |  |  | 0 | 0
3 | Secured Advance |  |  | 0 | 0
4 | Travel Reimbursement |  |  | 0
| Net Amount of Other Payments |  |  | 0 | 0
| Service Tax ON Other Payments, if any. |  |  | 0 | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 95506 | 95506
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL