## Order
Scenario 1
Imported Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | Service Tax | Other | Installation Rate Total | Amount
A | 601000000 | LEED Consultancy Services | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0
1 | 601000000 | Payment Schedule | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | As advance on issuance of formal work order of appointment. (30%) | [8 empty] | Nos | 1 | 162000 | 20023.2 | 0 | 182023.2 | 182023.2
1.2 | 601000000 | On incorporation of various green requirements in the tender specifications & drawing. (30%) | [8 empty] | Nos | 1 | 162000 | 20023.2 | 0 | 182023.2 | 182023.2
1.3 | 601000000 | On the completion and preparation of the first level documentation,including comissioning report,ready for submission to IGBC for review,post installation at site. (30%) | [8 empty] | Nos | 1 | 162000 | 20023.2 | 0 | 182023.2 | 182023.2
1.4 | 601000000 | On comissioning of green building certification from IGBC. (10%) | [8 empty] | Nos | 1 | 54000 | 6674.4 | 0 | 60674.4 | 60674.4

## certification
Scenario 1
Imported Supply | [19 empty] | 0 | 0 | 0 | 0
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate |  |  |  |  | Certification
[13 empty] | Basic Rate | Service Tax Amount | Other | Installation Rate Total | Amount | COP Percentage | COP Quantity | COP Basic | COP Service TAX | COP Others | COP TOTAL
A | 601000000 | LEED Consultancy Services | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 601000000 | Payment Schedule | [8 empty] | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 601000000 | As advance on issuance of formal work order of appointment. (30%) | [8 empty] | Nos | 0.2 | 162000 | 20023.2 | 0 | 182023.2 | 36404.64 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 601000000 | On incorporation of various green requirements in the tender specifications & drawing. (30%) | [8 empty] | Nos | 0.3 | 162000 | 20023.2 | 0 | 182023.2 | 54606.96 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 601000000 | On the completion and preparation of the first level documetation,including comissioning report,ready for submission to IGBC for review,post installation at site. (30%) | [8 empty] | Nos | 0.3 | 162000 | 20023.2 | 0 | 182023.2 | 54606.96 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 601000000 | On comissioning of green building certification from IGBC. (10%) | [8 empty] | Nos | 0.2 | 54000 | 6674.4 | 0 | 60674.4 | 12134.88 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
FOOTSTEPS OF BUDDHA HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:-FBHPL/ |  |  |  |  | Date.:- 10/12/2014
Project Code:- |  | 001 |  |  | Not For Payment
Project:- |  | Bodhgaya - Resort and Convention Centre at Bodhgaya
Work: | LEED CONSULTANCY |  |  | M/s En3 Sustainability Solutions Pvt Ltd.
Budget Code:- |  |  |  | New 126,Habibulah Road, T. Nagar Chennai-600017
W.O. / P.O. No. & Date:- |  |  | FBHPL/001/WO/11-12/C-007 Dated : 19.05.2010 | PAN No.:- AACCE0466B
Original W.O. Value:- |  |  | 540000 | VAT No.:- CST NO- Service Tax No:- AACCEO466BST001
WO Amendment No.:- |  |  |  | Invoice No. dated
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R001
A | Work Done Amount
1 | Net Supply Amount |  |  |  | 0 | 0
2 | Service tax |  |  |  | 0 | 0
3 | VAT |  |  |  | 0 | 0
4
5
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 0 | 0
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 0 | 0
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By
Sujit |  | Shilpa Kulkarni |  | Uttam Dalvi
QS and Contracts |  | Manager-Planning & Coordination |  | AGM -Project
CHPL
CHPL
FBHPL