## Order
Scenario 3
Local Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY | RATE (can be entered directly or summed up for totals)
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Local supply rate | [5 empty] | Installation Rate |  |  |  | Amount
[13 empty] | Basic Rate | Excise | Subtotal = Basic + Excise | VAT/CST on Subtotal | Others | Supply Rate Total (sum or direct entry) | Basic Rate | Service Tax | Other | Installation Rate Total (sum or direct entry) | LOCAL SUPPLY AMOUNT | INSTALLATION AMOUNT | TOTAL AMOUNT
1 | 401060202 | Supply, Fabrication, Installation Of 162 MM Thick (In place of 230mm thk wall) Plasmolite Interna including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 810 | 304.0344 | 0 | 304.0344 | 38.0043 | 0 | 342.0387 | 101.3448 | 12.5262 | 0 | 113.871 | 277051.3521 | 92235.5257 | 369286.8778
2 | 401060202 | Supply, Fabrication, Installation Of 112 MM (In place of 150mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc Complete. | [8 empty] | Sqft | 1150 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 384921.7176 | 128147.568 | 513069.2856
3 | 401060202 | Supply, Fabrication, Installation Of 112 MM (In place of 115mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 291 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 97401.9303 | 32426.9063 | 129828.8366

## Certification
Scenario 3
Local Supply + Installation | [24 empty] | 1012185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY | RATE (can be entered directly or summed up for totals)
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Local supply rate | [5 empty] | Installation Rate |  |  |  | Amount |  |  | LOCAL SUPPLY CERTIFICATION | [7 empty] | INSTALLATION CERTIFICATION |  |  |  | CERTIFICATION TOTAL
[13 empty] | Basic Rate | Excise | Subtotal = Basic + Excise | VAT/CST on Subtotal | Others | Supply Rate Total (sum or direct entry) | Basic Rate | Service Tax | Other | Installation Rate Total (sum or direct entry) | LOCAL SUPPLY AMOUNT | INSTALLATION AMOUNT | TOTAL AMOUNT | COP Percentage | COP Quantity | COP Supply Basic | COP Excise | COP Sub Total | COP VAT / CST | COP SupplyOthers | COP Supply Total | COP Installation Basic | COP Service TAX | COP Others | COP Installation Total | TOTAL COP AMOUNT
1 | 401060202 | Supply, Fabrication, Installation Of 162 MM Thick (In place of 230mm thk wall) Plasmolite Interna including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 810 | 304.0344 | 0 | 304.0344 | 38.0043 | 0 | 342.0387 | 101.3448 | 12.5262 | 0 | 113.871 | 277051.3521 | 92235.5257 | 369286.8778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 401060202 | Supply, Fabrication, Installation Of 112 MM (In place of 150mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc Complete. | [8 empty] | Sqft | 1150 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 384921.7176 | 128147.568 | 513069.2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 401060202 | Supply, Fabrication, Installation Of 112 MM (In place of 115mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 291 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 97401.9303 | 32426.9063 | 129828.8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:- |  |  |  |  | Date.:- 13/09/2014
Project Code:- |  | 006 |  |  | Not For Payment
Project:- |  | Proposed Five Star Hotel at Lucknow
Work: | Supplying,fabrication,installation and foam concreting for plasmolite internal walls for mockup |  |  | M/s. Fabtech Sterling Building Technologies Pvt .Ltd
Budget Code:- |  |  |  | 402/403. Vishakha arcade,Opp. Courtyard Hotel,Behind Mogaveera Bhavan school,Off. Veera Desai Road,Andheri (West) Mumbai:400053
W.O. / P.O. No. & Date:- |  |  | CHPL/006/WO/14-15/0559 Dated : 01-07-2014 | PAN No.:- AABCF5525B
Original W.O. Value:- |  |  | 1012185 | VAT No.:- CST NO- Service Tax No:- AABCF5525BSD002
WO Amendment No.:- |  |  |  | Invoice No. FSBT/MH/CHPL/2014-15/1
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
Certificate Type:-
Certificate No.:-
A | Work Done Amount
1 | Net Supply Amount |  |  |  | 0 | 0
2 | Net Installation Amount |  |  |  | 0 | 0
3 | VAT |  |  |  | 0 | 0
4 | Service Tax. |  |  |  | 0 | 0
5 | Supply and Installation Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 0 | 0
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 0 | 0
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL