## Order
Scenario 3
Local Supply
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY | RATE (can be entered directly or summed up for totals)
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Local supply rate | [5 empty] | Installation Rate |  |  |  | Amount
[13 empty] | Basic Rate | Excise | Subtotal = Basic + Excise | VAT/CST on Subtotal | Others | Supply Rate Total (sum or direct entry) | Basic Rate | Service Tax | Other | Installation Rate Total (sum or direct entry) | LOCAL SUPPLY AMOUNT | INSTALLATION AMOUNT | TOTAL AMOUNT
1 | 401010000 | Supply, Fabrication, Installation Of 162 MM Thick (In place of 230mm thk wall) Plasmolite Interna including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 810 | 304.0344 | 0 | 304.0344 | 38.0043 | 0 | 342.0387 | 101.3448 | 12.5262 | 0 | 113.871 | 277051.3521 | 92235.5257 | 369286.8778
2 | 401010000 | Supply, Fabrication, Installation Of 112 MM (In place of 150mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc Complete. | [8 empty] | Sqft | 1150 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 384921.7176 | 128147.568 | 513069.2856
3 | 401010000 | Supply, Fabrication, Installation Of 112 MM (In place of 115mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 291 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 97401.9303 | 32426.9063 | 129828.8366

## Certification
Scenario 3
Local Supply + Installation |  |  | COP-R001 | [21 empty] | 1012185 |  |  | 600256.364 | 0 | 600256.364 | 75032.0455 | 0 | 675288.4095 | 200085.4547 | 24730.5622 | 0 | 224816.0169 | 900104.4264
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY | RATE (can be entered directly or summed up for totals)
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Local supply rate | [5 empty] | Installation Rate |  |  |  | Amount |  |  | LOCAL SUPPLY CERTIFICATION | [7 empty] | INSTALLATION CERTIFICATION |  |  |  | CERTIFICATION TOTAL
[13 empty] | Basic Rate | Excise | Subtotal = Basic + Excise | VAT/CST on Subtotal | Others | Supply Rate Total (sum or direct entry) | Basic Rate | Service Tax | Other | Installation Rate Total (sum or direct entry) | LOCAL SUPPLY AMOUNT | INSTALLATION AMOUNT | TOTAL AMOUNT | COP Percentage | COP Quantity | COP Supply Basic | COP Excise | COP Sub Total | COP VAT / CST | COP SupplyOthers | COP Supply Total | COP Installation Basic | COP Service TAX | COP Others | COP Installation Total | TOTAL COP AMOUNT
1 | 401010000 | Supply, Fabrication, Installation Of 162 MM Thick (In place of 230mm thk wall) Plasmolite Interna including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 810 | 304.0344 | 0 | 304.0344 | 38.0043 | 0 | 342.0387 | 101.3448 | 12.5262 | 0 | 113.871 | 277051.3521 | 92235.5257 | 369286.8778 | 100 | 800 | 243227.5245 | 0 | 243227.5245 | 30403.4406 | 0 | 273630.9651 | 81075.8415 | 10020.974 | 0 | 91096.8155 | 364727.7806
2 | 401010000 | Supply, Fabrication, Installation Of 112 MM (In place of 150mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc Complete. | [8 empty] | Sqft | 1150 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 384921.7176 | 128147.568 | 513069.2856 | 100 | 1000 | 297524.0329 | 0 | 297524.0329 | 37190.5041 | 0 | 334714.537 | 99174.6776 | 12257.9902 | 0 | 111432.6678 | 446147.2048
3 | 401010000 | Supply, Fabrication, Installation Of 112 MM (In place of 115mm thk wall) Thick Plasmolite Internal Walls Including Pouring Of Light Weight Concrete And Also Including The Cost Of Sheets & All Materials Tools, Equipments, Consumables, Labours Etc. Complete. | [8 empty] | Sqft | 291 | 297.524 | 0 | 297.524 | 37.1905 | 0 | 334.7145 | 99.1747 | 12.258 | 0 | 111.4327 | 97401.9303 | 32426.9063 | 129828.8366 | 100 | 200 | 59504.8066 | 0 | 59504.8066 | 7438.1008 | 0 | 66942.9074 | 19834.9355 | 2451.598 | 0 | 22286.5336 | 89229.441

## COP Fasheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:- |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | NEH |  |  | Not For Payment
Project:- |  | NE HOTEL
Work: | Supply, Installation, testing & commisioning of low side HVAC work |  |  | M/s Perfect Infra Engineering Ltd.
Budget Code:- |  |  |  | #812, Ground floor, 8th A main, 23 cross, 7 sectors, HSR layout, Bangalore 560095
W.O. / P.O. No. & Date:- |  |  | CHPL/002/WO/10-11/0050 Dated : 19.05.2010 | PAN No.:- AABCP0122A
Original W.O. Value:- |  |  | 1012185 | VAT No.:- 29790851674 CST NO- 27740016613C Service Tax No:- ST/M-11/MRS/REGN/757610
WO Amendment No.:- |  |  |  | Invoice No.
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
Certificate Type:-
Certificate No.:-
A | Work Done Amount
1 | Net Supply Amount |  |  |  | 600256.364 | 600256.364
2 | Net Installation Amount |  |  |  | 200085.4547 | 200085.4547
3 | VAT |  |  |  | 75032.0455 | 75032.0455
4 | Service Tax. |  |  |  | 24730.5622 | 24730.5622
5 | Supply and Installation Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 900104.4264 | 900104.4264
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 900104.4264 | 900104.4264
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL