## Order
Scenario 4
Single rate for supply + install
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 203010000 | Providing and laying Brick siling including dressing & levelling and filling of joints by sand, the thickness of soiling will be 200 mm thick complete with compaction and also satisfaction of Engineer incharge | [8 empty] | LS | 1 | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000

## Certification
Scenario 4
Single rate for supply + install |  |  | COP-R001 | [18 empty] | 25000 | 0 | 0 | 0 | 0 | 25000
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 203010000 | Providing and laying Brick siling including dressing & levelling and filling of joints by sand, the thickness of soiling will be 200 mm thick complete with compaction and also satisfaction of Engineer incharge | [8 empty] | LS | 1 | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 100 | 1 | 25000 | 0 | 0 | 0 | 0 | 25000

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:- COP-R001 |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 006 |  |  | Not For Payment
Project:- |  | Proposed Five Star Hotel at Lucknow
Work: | Providing and laying Brick Soiling |  |  | M/s. Rajtara Construction
Budget Code:- |  |  |  | Pure Kauhali, PO-Chiluli, Tehsil-Tiloi, Distt- C.S.M.Nagina (U.P)
W.O. / P.O. No. & Date:- |  |  | CHPL/006/WO/13-14/Site/029 Dated : 19.05.2010 | PAN No.:- ATNPM4148D
Original W.O. Value:- |  |  | 25000 | VAT No.:- CST NO- Service Tax No:-
WO Amendment No.:- |  |  |  | Invoice No. dated 10th July 2014
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply and Installation Amount |  |  |  | 25000 | 25000
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 25000 | 25000
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement |  |  |  | 0
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 25000 | 25000
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL