## Order
Scenario 4
Single rate for supply + install
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 204030000 | Centering and Shuttering-Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 5.85m i.e. additional 2.35m over initial height of 3.5m. (At First Floor level) | [8 empty] | Nos | 10 | 50 | 10 | 10 | 5 | 0 | 75 | 750
a | 204030000 | Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 6.15m i.e. additional 2.65m over initial height of 3.5m. (At First Floor level - Kitchen area) | [8 empty] | Nos | 10 | 100 | 15 | 20 | 10 | 5 | 150 | 1500
| 204030000 | Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 6.85m i.e. additional 3.35m over initial height of 3.5m. (At Twelvth Floor level - Presidential Suite) | [8 empty] | Nos | 10 | 50 | 10 | 10 | 5 | 0 | 75 | 750
| 601000000 | description 4 | [8 empty] | Nil | 0 | 100 | 15 | 20 | 10 | 5 | 150 | 0
5 | 601000000 | Geo Technical Consultancy- Review of requirement of Pile Shoring Wall Design. | [8 empty] | Nos | 10 | 200 | 20 | 5 | 2 | 7 | 234 | 2340

## Certification
Scenario 4
Single rate for supply + install | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 204030000 | Centering and Shuttering-Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 5.85m i.e. additional 2.35m over initial height of 3.5m. (At First Floor level) | [8 empty] | Nos | 10 | 50 | 10 | 10 | 5 | 0 | 75 | 750 |  |  | 0 | 0 | 0 | 0 | 0 | 0
a | 204030000 | Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 6.15m i.e. additional 2.65m over initial height of 3.5m. (At First Floor level - Kitchen area) | [8 empty] | Nos | 10 | 100 | 15 | 20 | 10 | 5 | 150 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 204030000 | Centering and Shuttering-Staging / additional height in centering, shuttering upto a total height of 6.85m i.e. additional 3.35m over initial height of 3.5m. (At Twelvth Floor level - Presidential Suite) | [8 empty] | Nos | 10 | 50 | 10 | 10 | 5 | 0 | 75 | 750 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 601000000 | description 4 | [8 empty] | Nil | 0 | 100 | 15 | 20 | 10 | 5 | 150 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 601000000 | Geo Technical Consultancy- Review of requirement of Pile Shoring Wall Design. | [8 empty] | Nos | 10 | 200 | 20 | 5 | 2 | 7 | 234 | 2340 |  |  | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:-HAMPI/280 |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 002 |  |  | Not For Payment
Project:- |  | Hyatt Place -Hampi
Work: | Supply, Installation, testing & commisioning of low side HVAC work |  |  | M/s Perfect Infra Engineering Ltd.
Budget Code:- |  |  |  | #812, Ground floor, 8th A main, 23 cross, 7 sectors, HSR layout, Bangalore 560095
W.O. / P.O. No. & Date:- |  |  | CHPL/002/WO/10-11/0050 Dated : 19.05.2010 | PAN No.:- AABCP0122A
Original W.O. Value:- |  |  | 6905433 | VAT No.:- 29790851674 CST NO- 27740016613C Service Tax No:- ST/M-11/MRS/REGN/757610
WO Amendment No.:- |  |  |  | Invoice No. BLR-007/2010 dated 22 nd Dec 2010
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply and Installation Amount |  |  |  | 0 | 0
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 0 | 0
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement |  |  |  | 0
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 0 | 0
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL