## Order
Scenario 4
Single rate for supply + install
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount
1 | 102000000 | Providing & fixing of fencing work of Balli post of 10 ft. height & 5 ft. depth of normal dia (75-100mm) at every 3 mtr interval, and two horizontal bamboo (20 ft. long & dia 75mm) at the back side of GI sheets, & will be supported from back side of alternate inclined Balli after excavating the trench size 1x1x0.5 ft. ( when ever required) with plain cement aggregate of 1:5:10 at base complete as per approved drawing & design. The Balli posts to be fixed with three GI Corrugated sheets ( horizontally as per approved plan) of size 12x2.75 ft. with the thickness of 0.35mm , including all necessary hardwares, nails, warsal, Bamboo, Balli ,T&P labour etc. complete in all respect. (Rate is excluding of GI Sheet) | [8 empty] | RM | 250 | 600 | 0 | 0 | 0 | 0 | 600 | 150000
1.1 | 102000000 | Supply of Bamboo 20ft Long | [8 empty] | Nos | 10 | 150 | 0 | 0 | 0 | 0 | 150 | 1500
2 | 102000000 | Supplying & fixing of gate of size 12x6 ft. with following specifications…1- Size of MS Angle- 35x5mm2- Size of Flat Patti -20x5mm3- Size of MS Supporting Pipe -2x2 inch ( Guage-18) 4- Size of Diagonal Angle-35x5mm5-MS Jali- 14 Gauge6- Bush- 2 pices7-Misc hardware & fitting like ( Handle, Holdfast etc.) complete with labour and painting of one coat of primer.8-Foundation work with PCC for hanging arrangement of gate. | [8 empty] | Nos | 2 | 15000 | 0 | 0 | 0 | 0 | 15000 | 30000

## Certification
Scenario 4
Single rate for supply + install | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | UNIQUE IDENTIFIERS | [8 empty] | UOM | QTY
Sr. No. | Item Range Code | Description | Area | Make | Model No./ Product Code | Tag/ Item No. | ITC HS Code | Country of Origin | Port of Loading | User defined column |  |  | Supply + Installation Rate | [6 empty] | CERTIFICATION
[13 empty] | Basic Rate | VAT | Service | CESS | Other | supply + Installation total | Amount | COP Percentage | COP Quantity | COP Basic | COP VAT | COP SERVICE | COP CESS | COP Others | COP TOTAL
1 | 102000000 | Providing & fixing of fencing work of Balli post of 10 ft. height & 5 ft. depth of normal dia (75-100mm) at every 3 mtr interval, and two horizontal bamboo (20 ft. long & dia 75mm) at the back side of GI sheets, & will be supported from back side of alternate inclined Balli after excavating the trench size 1x1x0.5 ft. ( when ever required) with plain cement aggregate of 1:5:10 at base complete as per approved drawing & design. The Balli posts to be fixed with three GI Corrugated sheets ( horizontally as per approved plan) of size 12x2.75 ft. with the thickness of 0.35mm , including all necessary hardwares, nails, warsal, Bamboo, Balli ,T&P labour etc. complete in all respect. (Rate is excluding of GI Sheet) | [8 empty] | RM | 250 | 600 | 0 | 0 | 0 | 0 | 600 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 102000000 | Supply of Bamboo 20ft Long | [8 empty] | Nos | 10 | 150 | 0 | 0 | 0 | 0 | 150 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 102000000 | Supplying & fixing of gate of size 12x6 ft. with following specifications…1- Size of MS Angle- 35x5mm2- Size of Flat Patti -20x5mm3- Size of MS Supporting Pipe -2x2 inch ( Guage-18) 4- Size of Diagonal Angle-35x5mm5-MS Jali- 14 Gauge6- Bush- 2 pices7-Misc hardware & fitting like ( Handle, Holdfast etc.) complete with labour and painting of one coat of primer.8-Foundation work with PCC for hanging arrangement of gate. | [8 empty] | Nos | 2 | 15000 | 0 | 0 | 0 | 0 | 15000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## COP Facesheet
CHARTERED HOTELS PVT. LTD.
CERTIFICATE OF PAYMENT
COP No.:-HAMPI/280 |  |  |  |  | Date.:- 27/07/2011
Project Code:- |  | 002 |  |  | Not For Payment
Project:- |  | Hyatt Place -Hampi
Work: | Supply, Installation, testing & commisioning of low side HVAC work |  |  | M/s Perfect Infra Engineering Ltd.
Budget Code:- |  |  |  | #812, Ground floor, 8th A main, 23 cross, 7 sectors, HSR layout, Bangalore 560095
W.O. / P.O. No. & Date:- |  |  | CHPL/002/WO/10-11/0050 Dated : 19.05.2010 | PAN No.:- AABCP0122A
Original W.O. Value:- |  |  | 6905433 | VAT No.:- 29790851674 CST NO- 27740016613C Service Tax No:- ST/M-11/MRS/REGN/757610
WO Amendment No.:- |  |  |  | Invoice No. BLR-007/2010 dated 22 nd Dec 2010
Amended WO/PO Value:-
Sr. No. | Description of Work |  |  | Previous Certified Amount INR | Current Certified Amount INR | Cumulative Certified Amount INR
| Certificate Type:- |  |  |  | I
| Certificate No.:- |  |  |  | R003
A | Work Done Amount
1 | Net Supply and Installation Amount |  |  |  | 0 | 0
2 | VAT |  |  |  | 0 | 0
3 | Service Tax. |  |  |  | 0 | 0
4 | CESS |  |  |  | 0 | 0
5 | Others |  |  |  | 0 | 0
A | Gross Amount for Work Done As per this Bill |  |  | 0 | 0 | 0
B | Recoveries:-
1 | Recovery of Advance (@13.333%)
2 | Recovery of water Charges for Water Consumed
3 | Recovery of Power ( For Electricity Consumed)
4 | Recovery of Monthly Advance ( if any)
5 | Recovery of unsecured Advance( Including Expired Bank Guarantee
6 | Recovery of Insurance Premium
7 | Debit for Non removing of debris
8 | Retention Amount (as per Contract Conditions 5%)
9 | Non Conformity of Concrete |  |  |  | 0
10 | Miscellaneous
B | Total Gross Recoveries:- |  |  | 0 | 0 | 0
C | Other Payments |  |  |  | 0
1 | Mobilisation Advance |  |  |  | 0
2 | Ad-Hoc Certification |  |  |  | 0
3 | Secured Advance |  |  |  | 0
4 | Travel Reimbursement |  |  |  | 0
| Net Amount of Other Payments |  |  |  | 0
| Service Tax ON Other Payments, if any. |  |  |  | 0
C | Gross Amount for Other Payments |  |  | 0 | 0 | 0
| Gross Certified as Per This Bill A-B+C |  |  |  | 0 | 0
Rs. (In Words):
Mode of Payment:-
Remarks:-
Prepared By |  | Checked By |  | Approved By | Approved By
QS and Contracts |  | Asst.GM - Contracts |  | GM -Project | GM -Contracts
CHPL
CHPL
CHPL