## Sheet1
COST MONITORING OF CHPL PROJECT HAMPI
COST MONITOR
PROJECT NAME: |  | HAMPI
NO OF KEYS |  | 115
PLOT AREA (SQ.FT.) |  | 419430
BUILT-UP AREA (SQ.FT.) |  | 107370.9
BUDGETED COST (Rs. Lacs) |  | 3238.372
BUDGETED COST PER KEY (Rs. Lacs) |  | 28.1598
NO OF BAYS |  | 122
BUDGETED COST PER BAY (Rs. Lacs) |  | 26.544
INCURRED COST TILL DATE (Rs. Lacs) |  | 3934.7384
S. No. | Cost Head | Target Budget |  | Name of Agency | Contract value | Cumulative certified till May, 2011 | Certified in June 2011 | Certified in July 2011 | Certified in August 2011 | Certified in September 2011 | Certified in October 2011 | Certified in November 2011 | Certified in December 2011 | Certified in January 2012 | Certified in February 2012 | Certified in March 2012 | Certified in April 2012 | Certified in May 2012 | Certified in June 2012 | Certified in July 2012 | Certified in August 2012 | Certified in September 2012 | Certified in October 2012 | Certified in November 2012 | Certified in December 2012 | Certified in January 2013 | Cumulative certified till Date | Uncommitted Costs | Estimated cost at Completion |  | Remarks
|  | Amount | Cost / Sft |  | Incl. Taxes | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS | Excl WCT/TDS |  | Amt in Lacs | Cost / Sft
|  | (Rupees Lacs) | (Rupees) |  | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) | (Rupees Lacs) |  | (Rupees Lacs) | (Rupees)
|  | A | B |  | C | i | ii | iii | iv | v | vi | vii | viii | viii | viii | viii | viii | viii | viii | viii | viii | viii | viii | viii | viii | viii | D | E | F = C + E | G
A | PRELIMINARIES | 30.5325 | 28.4365 |  | 62.4011 | 24.7859 | 1.0489 | 0.927 | 0.525 | 0 | 0.40795 | 0.44075 | 0.72435 | 0 | 0.68935 | 2.0681 | 0.2414 | 0.55005 | 4.7348 | 0 | 2.5175 | 4.1634 | 1.0155 | 5.9652 | 7.6986 | 0 | 58.5037 | 5 | 67.4011 | 62.7741 | Costs 'b' to 'i' are included in Administration and HO expenses. There is no consideration of on site labour charges.
a | Site Survey - Area, levels and boundry | 3.375 |  | INFINITUDE DESIGN | C: 0.25; i: 0.25 | [14 empty] | 0.25 |  | 0.25
b | Soil Investigation work
c | Temporary fencing, gates, approach works
d | Construction water supply | 4.05
e | Construction electricity supply
f | Telephone Charges
g | Site Security | 5.67
h | Site Office Establishment | 2.8125 | [28 empty] | Included in Administrative expenses
i | Insurances (CAR Policy) | 3.375
j | Shore Piling works
k | On site labour charges |  |  |  | 27.5583 | 8.7027 | 0.906 | 0.927 | 0.525 | 0 | 0.40795 | 0.44075 | 0.48435 | 0 | 0.52935 | 0.8617 | 0 | 0 | 0.75115 | 0 | 2.5175 | 0 | 1.0155 | 5.9652 | 0 | 0 | 24.0342 | 2 | 29.5583 |  | Expenses not considered in budget.
|  |  |  | Balaram BK | 10.4352 | 8.0772 | 0.906 | 0.927 | 0.525 | [17 empty] | 10.4352 |  | 10.4352 |  | Cumulative certified till date considered as contract value.
|  |  |  | KGN ENTERPRISES | C: 0.6255; i: 0.6255 | [14 empty] | 0.6255 |  | 0.6255
|  |  |  | IMMANUEL ENTERPRISES | C: 9.7765; vi: 0.40795; vii: 0.44075 | 0.48435 |  | 0.52935 | 0.8617 |  |  | 0.75115 |  | 1.5156 |  |  | 4.7865 |  |  | 9.7774 |  | 9.7765
|  |  |  | Active Servicess | C: 6.4475 | [8 empty] | 1.0019 |  | 1.0155 | 1.1787 |  |  | 3.1961 | 2 | 8.4475 |  | Deep cleaning services
|  |  |  | Tirumala Enterprises | C: 0.2736 | [14 empty] | 0 |  | 0.2736 |  | Shifting of material- labour supply
l | Mock Up | 11.25 |  |  | 15.9761 | 15.8331 | 0.14294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9761 |  | 15.9761
|  |  |  | AMIT INTERIORS | C: 2.9381; i: 2.9381 | [14 empty] | 2.9381 |  | 2.9381 |  | Contract fore closed. Cumulative certified till date considered as contract value.
|  |  |  | JK ENTERPRISES (loose furniture) | C: 4.6316; i: 4.6316 | [14 empty] | 4.6316 |  | 4.6316 |  | Expenses for mock up done by JK Enterprises is considered in complete Guest room costs.
|  |  |  | PHOENIX ENTERPRISES | C: 1.0639; i: 1.0639 | [14 empty] | 1.0639 |  | 1.0639 |  | Contract fore closed. Cumulative certified till date considered as contract value.
|  |  |  | BOUGHT OUT ITEMS | C: 4.0615; i: 3.9186; ii: 0.14294 | [14 empty] | 4.0615 |  | 4.0615 |  | Cumulative certified till date considered as contract value.
|  |  |  | JK ENTERPRISES (Corridor) | C: 3.2809; i: 3.2809 | [14 empty] | 3.2809 |  | 3.2809 |  | Cumulative certified till date considered as contract value.
m | Miscellaneous |  |  |  | 18.6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.16 | 1.2064 | 0.2414 | 0.55005 | 3.9836 | 0 | 0 | 4.1634 | 0 | 0 | 7.6986 | 0 | 18.2434 | 3 | 21.6167
|  |  |  | Immanuel Enterprises | C: 6.2214 | 0.24 |  |  | 1.2064 | 0.2414 | 0.55005 | 3.9836 | [7 empty] | 6.2214 |  | 6.2214 |  | Removing the debris from site
|  |  |  | Sri Annapurneshwari Construction | C: 11.862 | [9 empty] | 4.1634 |  |  | 7.6986 |  | 11.862 | 3 | 14.862 |  | Supply of Manpower & M/c for misc work
|  |  |  | Sri Annapurneshwari Construction | C: 0.3733 | [14 empty] | 0 |  | 0.3733 |  | Additional scope of works ( internal shifting , Hydro Machine)
|  |  |  | Immanuel Enterprises | C: 0.16 |  |  | 0.16 | [11 empty] | 0.16 |  | 0.16 |  | Basement excavation works