## ERP
is
COST MONITOR
PROJECT NAME: |  |  | Hyatt Regency Lucknow
NO OF KEYS | 203 | [6 empty] | 491495455.38
PLOT AREA (SQ.FT.)
BUILT-UP AREA (SQ.FT.) | 309701
BUDGETED COST (Rs.) | 1983224245
BUDGETED COST PER KEY (Rs.) | 9769578
NO OF BAYS | 238
BUDGETED COST PER BAY (Rs.) | 8332875
INCURRED COST TILL DATE (Rs.) | 0
BUDGET CODE | MASTER CODES | COST HEAD DESCRIPTION | TARGET BUDGET |  | PURCHASE/WORK ORDER NUMBER | NAME OF AGENCY | CONTRACT VALUE | CUMULATIVE CERTIFIED TILL DATE | UNCOMMITTED COSTS |  |  | FORECAST COST AT COMPLETION | BALANCE WORK TO BE DONE | ITEM USED FOR DATATREIS
|  |  | AMOUNT | COST/SFT |  |  | Incl. Taxes
|  |  | (Rupees) | (Rupees) |  |  | (Rupees) | (Rupees) | POTENTIAL VARIATION | UNCOMMITTED CONTRACT/PO | TOTAL | (Rupees) | (Rupees)
|  |  | A | B |  |  | C | D | E | F
10 | 100000000 | Preliminaries | 4165364 | 13 |  |  | 991084 | 995463 | 0 | 0 | 0 | 0 | 0
101 | 101000000 | Site Office | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 102000000 | Barricading | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 103000000 | Equipment/Furniture/Computers/Printers/Plotters | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 104000000 | Soil Investigation, Topographical Survey, etc surveys | 0 | 0 |  |  | 512804 | 357748 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000285 | M/s Cengrs Geotechnica Pvt. Ltd | 327972 | 327972 | 0 | 0 | 0 | 0 | 0 | 104/HRL_Final/1000285
0 | 0 | 0 | 0 | 1740 | HRL_Final/1000284 | M/s. A-one Test house | 184832 | 29775 | 0 | 0 | 0 | 0 | 0 | 104/HRL_Final/1000284
105 | 105000000 | Miscellaneous | 0 | 0 |  |  | 478279 | 606215 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000298 | M/s. Rajtara Construction | 321479 | 143915 | 0 | 0 | 0 | 0 | 0 | 105/HRL_Final/1000298
0 | 0 | 0 | 0 | 0 | HRL_Final/1000290 | M/s. Govind Electric Company | 156800 | 156800 | 0 | 0 | 0 | 0 | 0 | 105/HRL_Final/1000290
20 | 200000000 | Civil & Structure | 538810120 | 0 |  |  | 306004984 | 737636005 | 0 | 0 | 0 | 0 | 0
201 | 201000000 | Building Piling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20101 | 201010000 | Reinforced Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20102 | 201020000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20103 | 201030000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20104 | 201040000 | Structural Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20105 | 201050000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 202000000 | Earth Work | 0 | 0 |  |  | 12444757 | 35582042 | 0 | 0 | 0 | 0 | 0
20201 | 202010000 | Shore Pilling | 0 | 0 |  |  | 2310000 | 2310000 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000305 | M/s. Yakoob | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 20201/HRL_Final/1000305
0 | 0 | 0 | 0 | 0 | HRL_Final/1000292 | M/s. Irshad | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 20201/HRL_Final/1000292
0 | 0 | 0 | 0 | 0 | HRL_Final/1000286 | M/s. Ranga Rao | 1310000 | 1310000 | 0 | 0 | 0 | 0 | 0 | 20201/HRL_Final/1000286
0 | 0 | 0 | 0 | 0 | HRL_Final/1000282 | M/s. Tohid | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 20201/HRL_Final/1000282
20202 | 202020000 | Excavation and removal of Earth | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20203 | 202030000 | Backfilling | 0 | 0 |  |  | 4114082 | 3706224 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000295 | Hind Traders | 548575 | 546675 | 0 | 0 | 0 | 0 | 0 | 20203/HRL_Final/1000295
0 | 0 | 0 | 0 | 0 | HRL_Final/1000288 | M/s. MS Enterprises | 1192300 | 1192300 | 0 | 0 | 0 | 0 | 0 | 20203/HRL_Final/1000288
20204 | 202040000 | Anti Termite Treatment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20205 | 202050000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 203000000 | Substructure | 0 | 0 |  |  | 126879494 | 0 | 0 | 0 | 0 | 0 | 0
20301 | 203010000 | Plain Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20302 | 203020000 | Reinforced Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20303 | 203030000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20304 | 203040000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20305 | 203050000 | Masonary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20306 | 203060000 | Internal Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20307 | 203070000 | Waterproofing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20308 | 203080000 | Miscellaneous | 0 | 0 |  |  | 5386046 | 10551328 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 288 | HRL_Final/1000307 | M/s. Uttam Samal | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 20308/HRL_Final/1000307
0 | 0 | 0 | 0 | 0 | HRL_Final/1000301 | M/s. Kiz Enterprise | 541760 | 472205 | 0 | 0 | 0 | 0 | 0 | 20308/HRL_Final/1000301
0 | 0 | 0 | 0 | 0 | HRL_Final/1000297 | M/s. Rajtara Construction | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 20308/HRL_Final/1000297
0 | 0 | 0 | 0 | 0 | HRL_Final/1000296 | M/s. Rajtara Construction | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 20308/HRL_Final/1000296
0 | 0 | 0 | 0 | 0 | HRL_Final/1000287 | M/s. MS Enterprises | 288826 | 288826 | 0 | 0 | 0 | 0 | 0 | 20308/HRL_Final/1000287
204 | 204000000 | Superstructure | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20401 | 204010000 | Plain Cement Concrete | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20402 | 204020000 | Reinforced Cement Concrete | 0 | 103 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20403 | 204030000 | Shuttering & Centering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20404 | 204040000 | Reinforcement Steel | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20405 | 204050000 | Masonary | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20406 | 204060000 | Internal Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20407 | 204070000 | External Plastering | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20408 | 204080000 | Waterproofing | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20409 | 204090000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 300000000 | Façade | 89273647 | 1142 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 301000000 | Façade Works | 0 | 189 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 302000000 | Stone Cladding | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 303000000 | External Paint | 0 | 0 |  |  | 3281500 | 0 | 0 | 0 | 0 | 0 | 0
304 | 304000000 | Façade Cleaning System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 305000000 | Façade Lightning | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 306000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 400000000 | Landscaping | 32028013 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 401000000 | Hardscape | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40101 | 401010000 | Roads & Pavements | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40102 | 401020000 | Compound Wall & Gates | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40103 | 401030000 | External Lighting | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40104 | 401040000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 402000000 | Softscape | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 403000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 500000000 | MEP | 353742546 | 221 |  |  | 3281500 | 28841375 | 0 | 0 | 0 | 0 | 0
501 | 501000000 | Plumbing & Drainage | 58590505 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50101 | 501010000 | Sanitary Fittings and Fixtures Supply | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50102 | 501020000 | Sanitary Fittings and Fixtures Installation | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50103 | 501030000 | Water Supply ( Hot + Cold ) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50104 | 501040000 | Drainage (Interior + Exterior) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50105 | 501050000 | Pumps & Equipments | 0 | 276 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50106 | 501060000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
502 | 502000000 | Fire Fighting / Fire Protection System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50201 | 502010000 | Pumps & Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50202 | 502020000 | Fire Hydrants | 0 | 95 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50203 | 502030000 | Sprinklers | 0 | 42 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50204 | 502040000 | Fire Extinguishers | 0 | 61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50205 | 502050000 | Electrical work for Plumbing & Fire Fighting | 0 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50206 | 502060000 | Miscellaneous | 0 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
503 | 503000000 | Electrical Work | 68567514 | 4 |  |  | 81500 | 81500 | 0 | 0 | 0 | 0 | 0
50301 | 503010000 | HT Works | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50302 | 503020000 | LT Works | 0 | 13 |  |  | 81500 | 81500 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000289 | M/s A A Engg. Co | 81500 | 81500 | 0 | 0 | 0 | 0 | 0 | 50302/HRL_Final/1000289
50303 | 503030000 | Panels & DB | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50304 | 503040000 | Cables | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50305 | 503050000 | Miscellaneous | 0 | 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | 504000000 | HVAC Work | 85566814 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50401 | 504010000 | Chiller/AC Cooling Plant | 0 | 62 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50402 | 504020000 | FCU + Gate valves + PICV valves + Thermostats | 0 | 41 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50403 | 504030000 | HVAC Low-side Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | 505000000 | IBMS Works (BMS & Fire Alarm and securities) | 29500000 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
506 | 506000000 | Diesel Generator Set + HSD Tank | 13100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
507 | 507000000 | Hot Water / Steam - Heat Pump / Boilers | 18800000 | 1567 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
508 | 508000000 | Sewage Treatment Plant | 3200000 | 834 |  |  | 3200000 | 640000 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000300 | Gamani Engineering Pvt. Ltd | 3200000 | 640000 | 0 | 0 | 0 | 0 | 0 | 508/HRL_Final/1000300
0 | 0 | 0 | 0 | 0 | HRL_Final/1000283 | Gamani Engineering Pvt. Ltd | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 508/HRL_Final/1000283
509 | 509000000 | Water Treatment Plant | 1500000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
510 | 510000000 | Gas Bank | 1300000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
511 | 511000000 | Data & Voice Communication Head end Equipments | 15555114 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
512 | 512000000 | Master Antenna & Television Head end Equipments | 3885000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
513 | 513000000 | Public Address | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
514 | 514000000 | Closed Circuit Television | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
515 | 515000000 | Physical Security Control System | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
516 | 516000000 | Audio Visual System | 6403625 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
517 | 517000000 | Signage | 3675000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
518 | 518000000 | Elevators & Escalators | 19100974 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
519 | 519000000 | Mechanical Car Park | 12750000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
520 | 520000000 | Dimmer | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
521 | 521000000 | IT and Software | 12248000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
522 | 522000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 600000000 | Interior & Fitouts | 485343817 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601 | 601000000 | Guest Room Interiors | 258249094 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60101 | 601010000 | Guest Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010101 | 601010100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601010101 | 601010101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601010102 | 601010102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601010103 | 601010103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010102 | 601010200 | Fixed Furniture Works | 0 | 415 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010103 | 601010300 | Loose Furnitures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010104 | 601010400 | Furnishings | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010105 | 601010500 | Fixtures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010106 | 601010600 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010107 | 601010700 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60102 | 601020000 | Corridor including Lift Lobby | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010201 | 601020100 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601020101 | 601020101 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601020102 | 601020102 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
601020103 | 601020103 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010202 | 601020200 | Fixed Furniture Works | 0 | 318 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010203 | 601020300 | Loose Furnitures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010204 | 601020400 | Furnishings | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010205 | 601020500 | Fixtures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010206 | 601020600 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010207 | 601020700 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60103 | 601030000 | Mock-Up Room | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
602 | 602000000 | Public Area | 128554213 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60201 | 602010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6020101 | 602010100 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6020102 | 602010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6020103 | 602010300 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60202 | 602020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60203 | 602030000 | Loose Furnitures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60204 | 602040000 | Furnishings | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60205 | 602050000 | Fixtures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60206 | 602060000 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60207 | 602070000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
603 | 603000000 | BOH Area | 98540509 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60301 | 603010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6030101 | 603010100 | Flooring | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6030102 | 603010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6030103 | 603010300 | Ceiling | 0 | 129 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60302 | 603020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60303 | 603030000 | Loose Furnitures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60304 | 603040000 | Furnishings | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60305 | 603050000 | Fixtures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60306 | 603060000 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60307 | 603070000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
604 | 604000000 | Commercial Area | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60401 | 604010000 | Civil Finishes Works (Including Ceiling & Painting Works) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6040101 | 604010100 | Flooring | 0 | 291 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6040102 | 604010200 | Walling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6040103 | 604010300 | Ceiling | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60402 | 604020000 | Fixed Furniture Works | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60403 | 604030000 | Loose Furnitures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60404 | 604040000 | Furnishings | 0 | 551 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60405 | 604050000 | Fixtures | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60406 | 604060000 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60407 | 604070000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 700000000 | OS&E | 40000000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
701 | 701000000 | Linens / Uniforms | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
702 | 702000000 | Chinaware / Glassware / Silverware, Utensils, Staff Dinning | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
703 | 703000000 | Equipments | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70301 | 703010000 | Kitchen | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70302 | 703020000 | Laundry | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70303 | 703030000 | Gym & Spa | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70304 | 703040000 | Swimming Pool/Water Feature | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
704 | 704000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 800000000 | Consultancy & Others | 90073192 | 0 |  |  | 3932600 | 29819559 | 0 | 0 | 0 | 0 | 0
801 | 801000000 | Consultancy Fee | 0 | 0 |  |  | 3932600 | 29819559 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | HRL_Final/1000266 | M/s. Benjamin West India Pvt. LTD. | 3932600 | 786520 | 0 | 0 | 0 | 0 | 0 | 801/HRL_Final/1000266
0 | 0 | 0 | 0 | 0 | HRL_Final/1000271 | M/s Epicons Consultants Pvt. Ltd | 0 | 475779 | 0 | 0 | 0 | 0 | 0 | 801/HRL_Final/1000271
802 | 802000000 | Travelling Reimbersment | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
803 | 803000000 | Hits Fees | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
804 | 804000000 | Miscellaneous | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 900000000 | Project Running Expenses And Pre Opening Site Expenses | 170774722 | 578 |  |  | 130652 | 162978 | 0 | 0 | 0 | 0 | 0
901 | 901000000 | Salary | 0 | 291 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90101 | 901010000 | Site Staff Salary | 0 | 228 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90102 | 901020000 | Head Office Support Salary/Cost | 0 | 58 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
902 | 902000000 | Site Office -Running Expenses | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90201 | 902010000 | Travelling | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90202 | 902020000 | Reimbursable Expenses | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90203 | 902030000 | Rent | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90204 | 902040000 | Insurance | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90205 | 902050000 | Printing, Stationary, Courier | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90206 | 902060000 | Statutory Fees | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90207 | 902070000 | Security | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90208 | 902080000 | Miscellaneous | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
903 | 903000000 | Fees and Permits | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90301 | 903010000 | Legal Expenses | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90302 | 903020000 | Statutory Fees | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90303 | 903030000 | Liasioning Expenses | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
90304 | 903040000 | Insurance | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
904 | 904000000 | Pre-Opening Expenses | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
905 | 905000000 | Miscellaneous | 0.00 | 0.00 |  |  | 130652.21 | 130652.00 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
0 | 0 | 0 | 0 | 578.00 | HRL_Final/1000269 | Pest Control (India) Pvt Ltd. | 130652.21 | 130652.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 905/HRL_Final/1000269
A1 | A10000000 | Contingency | 179012822.03687 | 578.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
A11 | A11000000 | Contingency | 90210571.17585 | 291.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
A12 | A12000000 | Escalation | 70760136.62585 | 228.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
A13 | A13000000 | Tax and Labor Cess | 18042114.23517 | 58.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00
0 | 0 | Mandotory tex for datatreis | 0.00 | 0.00 |  |  | 0.0 | 0.0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00